## Slide 1: The Weald Courts 6 and 7 covered structure Working Group report to General Committee November 2020

## Slide 2: Background
In the summer of 2018, The Titcombe Foundation approached the Weald with the offer of a grant of £250,000 to fund covering Courts 6 and 7 with a permanent structure
This clearly presents an amazing opportunity to the Club and work has been undertaken by the previous committee to develop a proposal that fits within the budget available and terms of the grant
Key points:
  The funding is offered for this specific purpose only
  Various options have been investigated by the previous committee, however many were over budget
  The proposal from Fordingbridge, 1st Surface and Luminence Pro, is the only solution that has been found to be vaguely within any viaible budget by the previous committee
  The proposal includes increasing the size of the footprint of the courts to meet LTA recommended size requirements (currently they are not)
  The Titcombe Foundation has subsequently agreed to increase their grant offer to £300,000
  Courts 6 and 7 would require resurfacing in a couple of years regardless of any covering structure

## Slide 3: Working Group
The working group have met on two occasions and made various investigations to understand the proposed project and the progress made by the previous Weald committee
This has included:
  Clarification of contractors proposal and prices
  Determination of overall project costs
  Maintenance requirements and costs
  Planning consent and pre-application planning advice
  Potential fee/charging structures for use of the courts
  Potential booking priority system to manage use
  References from other Fordingbridge installations
  Discussions with disability tennis members
  Charities commission requirements
  LTA Loan Scheme
  Titcombe Foundation grant terms and conditions
  Collation and answering of Members questions

## Slide 4: Clarifications on proposal
Written questions were asked of the contractors and a subsequent meeting held via Zoom
Main concerns:
  Clarification of the scope of the proposals including design of structure and court sizes
  Breakdown of costs, clarification of what is included, what risks are excluded and remain with the Weald – how “fixed” are the current costs
  Contractual issues including how the three contractors are appointed and work together, the proposed form of contract/terms and conditions, warranties and liabilities

## Slide 5: Clarifications on proposal

## Slide 6: Clarifications on proposal - design
Fordingbridge have confirmed that they have liaised with the LTA on the design
However some concerns remain regarding whether the height of the structure meets LTA guidelines – 9m minimum over the net this needs clarifying asap
The footprint of courts 6 and 7 is to be increased to meet LTA recommended standards and better comply with Disability Discrimination Act (DDA) requirements
Some existing trees will require removal to accommodate the increased footprint. This will be to the north and west of the existing courts as there are tree preservation orders to the south and east.
Excess material from the excavations will be mounded into a bank that could provide seating for spectators check with David. From1st surface quote : “Site set up Heras fencing to compound area and working area. To the areas of extension which will be 2 metres to both sides of the courts and 1.82m to the far end we will dig out the topsoil and sub-soil to the required depth with all soil from the earthworks being spread on site. The soil banks will be graded, and we will remove the trees as needed to the lightly wooded area.”
Due to the increased footprint (and so increased run back and side run) it is not envisaged that ingress of rain through the open sides of the structure will be an issue for the playing area. If this it does prove to be a problem partial mesh walls could be added at a later date (at additional cost) costs requested from Fordingbridge
Cost from Adam 30/10/20 : The structure will require drainage in the form of soakaways – this has not been included in the design or costs thus far. The price for our Engineer to provide soakaway calculations and specification is £560.00 + VAT
Jonathans estimated cost for soak-away as per email 31.10.20 : We need to include a budget cost for the soakaway. I would allow £30k. 15k for one at each end
The costs currently are for a porous asphalt surface, clay is not recommended for DDA requirements or due to dust collecting on the structure and lights. Acrylic surface would add £23,000 to £25,000 to the costs and there are concerns that it would be unplayable should it become wet.
It is not envisaged that the floodlights will be required during normal daylight hours, due to the opaque fabric cladding.
The new lighting will utilise the existing cabling from the clubhouse to courts 6&7, this is assumed to be sufficient, but has not been specifically confirmed.

## Slide 7: Clarifications on proposal - costs
Each of the contractors has have been asked to provide a detailed breakdown detailing what is included within their costs, what risks they have priced to include?, and what risks remain with the Weald?
Insert cost info when we get it. Joey: We have all 3 quotes now, all on gmail
All three contractors have verbally confirmed that they will hold their prices for a period of 12 months from submission of a planning application needs to be confirmed in writing
Fordingbridge have also been asked to provide indicative maintenance costs add in when we receive. Joey: I have added this into the maintenance section
Fordingbridge have advised that upfront design costs to cover the necessary work to submit for pre-planning application advice would be £2,500. This would be deducted from the total cost when the project proceeds

## Slide 8: Clarifications on proposal - contract
The current proposal provides for the Weald to separately engage each contractor under their own terms and conditions.
The contractors say they are comfortable with this way of working and will work together.
Whilst it is understood why this has been proposed as a cost saving measure, the working group have considerable concerns that this is not the correct way to proceed and that it exposes the club to unnecessary risk, and may result in a greater out-turn cost.
It is the view of the working group that there should be a single company appointed as principle designer responsible for coordinating the various elements of the design to ensure that it all fits together, otherwise this risk will sit with the Club.
Likewise there also needs to be a principle contractor on site who will take overall responsibility for the construction of the project and coordinate the other contractors work into the programme. Without a principle contractor the Club will take on this role by default along with the risks that this presents, should for example a delay to the groundworks cause a knock on effect to the erection of the structure by a different contractor.
Aside from the risk considerations, there is a legal obligation for the Weald as Client to appoint a principle designer and a principle contractor with overall responsibility for the site safety under the Construction (Design and Management (CDM) regulations, that will apply to this project.
Fordingbridge have been asked to provide their costs to take on the roles of principle designer and principle contractor both under the CDM regulations and also to coordinate the design and construction elements of the project. Email from Adam 30.10.20 “In this scenario, as Fordingbridge will assume the full risk for this project for the duration of the works being undertaken and thereafter, there is a significant cost uplift to the overall project value of £276,984.00 + VAT. The cost for Fordingbridge to act as Principal Contractor for the duration of this project: £372,245.00 + VAT”
There would be an additional cost if we wished to engage the contractors under a more formal JCT contract rather than their own terms (although a JCT contract is considered more appropriate by the working group and is recommended by the LTA for such works).

## Slide 9: Project costs
Currently have Julie’s spreadsheet copied into tables that follow
Need to scope out full project costs when info is provided by contractors
Include planning, contingency, etc
Offset resurfacing costs that would be needed regardless of any structure (or is that from sinking fund?)
VAT recovery – Rob welcome your input here
Happy for someone better placed to present the costs and budget better!

## Slide 10: Project costs added in additional planning
Element | Details | Net Cost | VAT | Total cost
Planning approval | Pre-application advice consultant fees Pre-application design (£2,500 inc in Fordingbridge quote below) Pre-application advice Council fees Planning permission drawings Planning permission consultant fees Planning permission Council fees | £2,500 - £150 £995 £2,500 £7,854 | £500 - - £199 £500 - | £3,000 Inc below £150 £1,194 £3,000 £7,854
1st Surface | Foundations, surfacing, fencing and reinstatement | £88,645 | £17,729 | £106,374
Fordingbridge | 34m x 36.6m twin canopy | £163,549 | £32,710 | £196,259
Luminance Pro | Enabling works for lighting HiLux LED Lighting | £2,660 £22,130 | £4,958 | £29,748
Contingency | 10% | £28,500 | - | £28,500
Total |  | £319,483 | £56,596 | £376,079

## Slide 11: Project costs – funding – need to check
Available funding | Net | Vat | Total
Titcomb Foundation Grant | 300,000 | 0 | 300,000
Sinking Fund | 25,000 | 0 | 25,000
Total Available Funding | 325,000 | 0 | 325,000
Gross shortfall | 10,667 | (55,596) | (44,929)
VAT reclaim (33%) | 0 | 18,347 | 18,347
Net funding shortfall | 10,667 | (37,249) | (26,582)
Non-cash P&L expense w/off of floodlight hoods | 4,324 | 0 | 4,324

## Slide 12: Maintenance requirements and costs
A detailed Operations and Maintenance manual will be provided by Fordingbridge, however in summary:
Safe walking access will be provided through the central valley gutter
An inspection should be carried out once a year
This inspection may need to be more frequent dependant on potential gutter blockages (leaves from nearby trees)
15-20 years life expectancy for cladding.
Single span structure full re-clad cost –circa £9,000 + Vat (+ installation & plant)
Twin span structure full re-clad cost –circa £18,000 + Vat (+ installation & plant)
Price for Fordingbridge to undertake a full canopy clean, gutter inspection and subsequent un blockageas required:£4,136.00 + VAT (Price includes relevant plant, safety netting and is reviewed annually.) .
Joey: In my opinion, Fordingbridge’s price for cleaning and mainenance is overpriced and we could get a much more competitive price from a specialist contractor. However this should be factored in for the time being.

## Slide 13: Planning consent and pre-application advice
Planning permission will be required for the structure and this will be dealt with by Mid Sussex District Council.
Mid Sussex District Council offer a paid for service of “pre-application advice” which the working group strongly recommended should be utilised. This would provide formal written advice on the proposals and provide information on likely conditions that would be attached to any consent including the need for environmental surveys and/or flood risk assessment.
This will allow the detailed design to progress taking this formal advice into account which should make the subsequent planning application more straightforward.
To carry out the work necessary to make a request for pre application advice is likely to cost in the region of £5000, made up of £2,500 upfront design costs and £2,500 planning consultant fees to collate the required information and manage the process.
This amount will be at risk, should the project subsequently not proceed. Question from Joey: If the project does proceed will this amount be off-sit against the full planning cost? The foundation have indicated they may be willing to pay this for us up front?
Several members who are also residents of South Bank have already registered their intent to object to a planning application.

## Slide 14: Fee/charging structures
In order to replenish the Club’s sinking fund and to provide sufficient finances to cover future maintenance/replacement of the structure, the working group consider that there will need to be a charge for using the covered courts.
This has been a key topic from the members questions regarding the project.
We approached other local clubs with covered courts to find out what they charge (although it should be noted that airhalls have significantly greater operational costs than the structure proposed at the Weald).
It will be necessary to consider what charges will be levied to use the covered courts, how much this will be and whether the charges will apply year round or be seasonal to reflect demand.
This will need to strike a balance between replenishing the sinking fund to cover maintenance and replacement vs putting people off using the courts due to the additional costs (particularly during good weather)
Consideration also needs to be given to how the charge will be collected and/or access only given to those who have paid
I would suggest a flat fee £4 per hour with the exception of June, July, August where it will be free. Floodlight cost will need to be added.

## Slide 15: Booking priority considerations
Consideration will need to be given to how the courts are allocated when they are oversubscribed.
This has also been a key topic from the members questions
Considerations are needed around who would be given priority and how this would be managed
  Team matches
  Coaching sessions
  General member bookings
  Disability sessions
  Public use
We need to recognise that the courts are likely to be either members last choice in good weather (particularly if there is an extra charge to use them) whilst being in high demand during the winter and a balance needs to be struck as to how priority is allocated
Some members may see the courts being covered as a loss of facilities due to the relatively limited time that a cover is specifically required (as opposed to a nice to have benefit in the winter months to guarantee play)
However records from the boking system show that Courts 6 and 7 are already the least popular, with the lowest number of member bookings
Joey: I would suggest that these courts are given equal access to all aspects of the club. Due to lockdown the coaches were given priority to court 6 and 7 however this should be revoked once the structure is built, presuming there will be no COVID restrictions at this time. There should be some court allocation given to coaches but this will be in consultation with the tennis Committee. They will also need to be offered to the disability tennis session on Sunday afternoon and in use with any school events to meet the public use criteria. NB the coaches will need access to the remaining courts to ensure there is no disruption to their programme. Once agreed coaching, disability and public use

## Slide 16: References
“Apologies for the time to respond- School life is very challenging at present.Fordingbridge installed the cover for the MUGA at my school. The structure is brilliant and we are very pleased with the quality.
The site presented lots of challenges to the company and to be fair they did manage very well and were able to overcome the obstacles. I would use them again.
I hope that helps.--
Heather Landers, Headteacher
St Stephens (Saltash) Community Primary School ”
___________________________________________________________________________________________________________________________________________
“Email from Nick Reason: Wed 30/09/2020 18:05
Seems from the assistant manager at Notcutts, they love the canopies – they also have them at Tunbridge Wells (also by Fordingbridge) although slightly different as they trapped warm air there in the summer (they abutted a building) so they went for large auto-ventilation with the Ditchling ones, as too hot for plants. With more open sides, temperature not deemed an issue. Lighting also automated and it’s on when cloudy – their roofing is opaque. Assume the Weald will be without vents and on/off lighting control – can’t recall if roofing is clear?
She mentioned there was some minor water leakage from seals, but otherwise very positive.
From my layman’s view, they appear smart, well-designed and robust without there being too much ‘structure’ (forgive my terminology Jonathan J) – can’t imagine there would be too much in the way of maintenance cost other that winter cleaning, which would probably be via rope-access – I’d also think they would last a lot longer than 10 years – have we asked specifically the expected lifespan of the roof membrane material?”

## Slide 17: Discussions with disability tennis members
Nick was going to talk to them – add report if so :
Joey: Ian Maskell has emailed us, Nick you could always pick his brains? Ps I did reply to his original email:
From: Ian Maskell <ian.admarchitects@gmail.com> Sent: 09 October 2020 11:20 To: 'court6and7@gmail.com.' <court6and7@gmail.com.> Subject: question on court 6 and 7 project
Hi Court 6 and 7 covering project
Would you like me to comment on the detailed proposals as a club member, wheelchair user and architect ?
You can answer no, I promise not to cry.
Best.
Regards Ian Maskell
Ian J Maskell – Architect
admArchitects■com
Office address - Turners, 53 Hassocks Road, Hurstpierpoint, West Sussex, BN6 9QL, United Kingdom
M – 07850 865070
T – 01273 835043
E ian@admarchitects.com
W - instagram.com/admarchitects/

## Slide 18: Charities Commission
Email from Nick hill 19th Oct 2020
I’ve spoken to the Charities Commission help-desk – they advise it is for the Charity Trustees to determine that the donation (including the beneficiary and the development) meet with the agreed purpose & objectives of the Trust. There will be a governance document – a Trust Deed – that sets out the structure and modus of the charity, that would have been documented and agreed by the Trust and the Charity Commission at the time of establishment of the charity when Charity Commission approval & authority is sought & granted. They said it should be for the Trust to satisfy themselves that the donation aligns with the Trust Deed terms, and that there would be no onus on the Club to be satisfied. I would think those terms will have/should have been shared with the Club at least in principle, it appears it is for the Trustees to be satisfied with what’s planned, which may be what Clarissa is referring to?
The Club should presumably be satisfied that Trust Governance is met before proceeding with the Development, I would think the Trust Deed may be quite broad in its purpose.
Let me know if further needed at this stage.
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/586357/GD2.pdf

## Slide 19: LTA Loan scheme
To date it has been planned to cover the costs of the project from the Titcombe foundation grant and existing Weald finances
However the LTA do have an interest free loan scheme that could be utilised to top up costs if that were beneficial. The LTA have also identified Haywards Heath as an area of potential demand for a community indoor tennis centre.
Full details are available on the LTA website but in summary the LTA’s facility loan scheme provides interest free loans from £25,000 up to £250,000 and will prioritise investment into low cost indoor structures and floodlights to enable communities to grow participation by accessing all year round facilities. https://www.lta.org.uk/workforce-venues/tennis-venue-support/tennis-and-padel-facility-funding-and-advice/quick-access-loan-scheme/
Should we wish to pursue this possibility, then various conditions would need to be met, including complying with LTA technical and project management guidance and providing three tendered costs for the project via a JCT contract

## Slide 20: Clarifications on Titcombe Foundation grant
Members of the working group met with Titcombe foundation representatives on Sunday 1 November 2020
01.11.20 Joey to email Foundation with summery of zoom call. Will update.

## Slide 21: Working Group Summary
The offer of a grant to provide a cover to courts 6 and 7 is clearly very generous and provides a one off opportunity to the Club to enhance its facilities and offer to members
There are many constraints around what can be achieved but the working group are keen that the Club should make every effort to find a solution that allows us to accept the grant and provide covered court facilities within the available budget
However this should be a decision that is backed by the wider membership and the manner in which the project is taken forward should not expose the Club to unnecessary risk
There are still some aspects of the project that require clarification, particularly around the cost and affordability of the project and the specification of the design before we can be confident that an acceptable solution can be provided within budget
Joey to write summery to foundation and ask for feedback
We will need to explore JCT contracts, exterior project manager. Pre-application
We should have a look at whether it is possible to fit in 2 extra courts at the club? what the cost would be? As a comparison? Even if it is to rule this out.
We need to plan for full presentation to GC before next GC meeting (likely early December). This will need to include a full balance sheet including planning, project management fees, contingency, depreciation and VAT clawback. Possible video and shortened version of this presentation.
Possible vote before end of year.

## Slide 22: Working Group recommendations to GC
How do we think this should move forward? Suggestions below, but welcome others input please 
A members vote on the principle of accepting the grant and providing a cover to courts 6 and 7 has been promised, along with providing answers to the questions that have been raised.
There needs to be a summary presentation to members answering their questions and providing sufficient detail to allow them to cast their vote, whilst acknowledging that some of their questions cannot be answered at this time but that there will be further consultation should the project progress.
We should recognise that not all members appear to be in favour of the proposals and we should be prepared for challenge against the principle of the project, and the need to sell the concept to those who are opposed or sceptical.
Should the “in principle” vote be favourable, then work should commence on requesting pre-application planning advice. This will involve a cost of approx. £5,000 which will be non-refundable should the project not proceed.
Consultation on the principle of covering the courts should be carried out with our neighbours, to understand their concerns
Alongside this the project management and contract arrangements need to be confirmed in writing such that the risks to the Club are suitably managed
Conditions of the grant and the mechanism for receiving the funds needs to be agreed in writing
An overall project budget including contingency needs to be agreed
The specification of the structure needs to be checked as complying with LTA guidance
Consideration needs to be given to the operation and use policy for the courts (charges and priority)

## Slide 23: Members Questions
76 individual questions, submitted by 18 different members
However, on analysis they fall into 9 broader categories, with several questions on similar topics within those
  Consultation
  Planning
  Design
  Construction
  Project Management
  Costs
  Funding
  Operation
  Maintenance
The broad questions raised and proposed answers follow in the tables below

## Slide 24: Members Questions - Consultation
Question | Response
Several questions surrounding the process for submitting questions and information available to members | Members can submit questions via a dedicated email address court6and7@gmail.com The presentation given at the AGM is available at the following link https://drive.google.com/file/d/1ejqtKUfo6KjemYmOctT9Zqm9lWNawogO/view The responses to these general questions will be shared with members
Lack of member consultation thus far | We appreciate that limited information has been made available to members so far, however some work was necessary before a concept could be presented. It is not a fait acompli, and there will be a members vote to determine if members wish the project to be developed further. If the vote is yes, then further work will be undertaken and members will be consulted further and kept informed as the scheme develops.
Has any consultation been carried out with our neighbours yet? | No consultation has been carried out with local residents as yet, but if the result of the members poll is supportive of proceeding with the project then we will consult with our neighbours shortly thereafter, as we appreciate they will be interested and have views that need to be considered.

## Slide 25: Members Questions – Planning
Question | Response
Various questions surrounding planning permission | Planning permission will be required, but no formal discussions have been held yet The first step in the process would be to submit a request for “pre-application advice” This would give a good indication of whether a full application would be successful and if so what conditions may apply Making a request for pre-application advice would likely cost in the region of £5000 to cover upfront design Making a full planning application would cost in the region of £XXXXX These costs would be up front and at risk as there is no guarantee that planning permission will be granted It is likely that some residents of South Bank (and possibly other neighbours) may formally object to the application, no consultation has been carried out with our neighbours as yet but will be needed if we proceed

## Slide 26: Members Questions - Design
Question | Response
Need for floodlights | Luminance Pro have advised that the use of floodlights should not generally be required during daylight hours and have confirmed that the lighting has been designed to the relevant standards
Previous use of structure | There are many examples of this specific type of structure including at Notcutts garden centre in Ditchling. The working group have visited Notcutts and spoken with the management who report they are very happy with their canopys. Other references from Fordingbridge customers have also been favourable This type of structure has been used to cover multi-use games areas, however they have not yet specifically been used in a tennis club setting.
Why is a tarmac court surface proposed | The Foundation requires that the courts are accessible to disability tennis, and LTA guidance recommends hard or acrylic courts for this purpose. Additionally, dust from clay courts would rise and stick to the roof fabric and lighting, causing a maintenance issue. **Does this apply with artificial clay??? CHECK The proposal includes for courts 6 and 7 to be increased in size and re-laid in porous asphalt to match our existing courts 2, 3, 4 and 5. To lay acrylic courts would increase the cost by £23,000 to £25,000 and concerns have been raised should they get wet from rain ingress

## Slide 27: Members Questions - Design
Question | Response
Concerns that with no walls the rain/wind will come in and make the courts unplayable | The contractors do not consider this to be a significant problem, due to the proximity of the surrounding trees and given that increasing the court footprint will provide greater run back and side runs to the playing area. If this is a problem, then an additional mesh could be installed along the sides **Need cost for this
Court size specification | The courts are to be increased in size to comply with LTA recommended requirements – this increases the court footprint from the current courts which do not meet that specification
Various other more detailed design questions | Not possible to give answers at this time, but the issues raised will be addressed should the project proceed to detailed design stage.

## Slide 28: Members Questions - Construction
Question | Response
How long is the construction phase | The erection of the structure will take 2-3 weeks, but groundworks will be required in advance of this and surfacing and installation of lighting will follow after, so approximately 6-8 weeks construction in total. The macadam surface then has to left to cure for 3 weeks before it can be painted with the final surface and so courts 6 and 7 are likely to be out of action for around 10-12 weeks whilst the project is completed.
Is the surfacing contractor a member of SAPCA? (as recommended by the LTA) | 1st surface are not members of SAPCA, however the Weald have previously worked with them on the recent resurfacing of Court1/mini tennis courts
Various other more detailed site and construction questions | Not possible to give answers at this time, but the issued raised will be addressed should the project proceed to the construction stage.

## Slide 29: Members Questions – Project Management
Question | Response
What are the contract/sub contract arrangements | The current proposal provides for each contractor to be engaged separately, however the working group advise this is not the best way to proceed due to the risks to the Club and have asked the contractors to provide their costs for taking on the role of principle designer and principle contractor and managing and coordinating the design and construction phases.
Clarification of costs, what is included/excluded, where do project risks sit | This has been discussed with the contractors and further information has been requested to clarify – Update once info received
How many companies were considered for the project | A number of other companies were approached to provide a structure, but their solutions exceeded the budget available. The Fordingbridge solution is the only one that has been found to be vaguely within budget
Questions around warranties | The contractors have been asked to clarify – Update once info received
Questions around Weald management | A working group has been set up to review the work undertaken by the previous committee and to take forward the project

## Slide 30: Members Questions – Costs
Question | Response
Clarification and breakdown of costs, including understanding if the costs are “fixed” at this stage | The contractors have been asked to clarify, exactly the scope of their proposals, what is included/excluded, which risk they have priced for an included and what risks remain with the Weald. With this information the working group will prepare an overall project budget to include seeking planning permission, contingencies etc

## Slide 31: Members Questions – Funding
Question | Response
Is a LTA loan available? | An LTA loan may be available, however this is not something that has been considered for the project yet.
What conditions are attached to the Titcombe Foundation grant? | Clarify after meeting them on Sunday : Joey to email summery
How will the club replenish the sinking fund? | Needs consideration alongside the charging structure £25,000 of the sinking fund had been allocated to resurfacing Courts 6 and 7, and this amount will be used to part fund the project Working Group/Weald GC to consider how to replenish.
Does the club have additional funds to put to the project? | Will become clearer when costs/finances are reviewed Working Group/Weald GC to consider

## Slide 32: Members Questions – Operation
Question | Response
Will there be a charge for members to use the courts? (raised 4 times) | Needs consideration of options and GC decision
How will court bookings be prioritised? (raised 5 times) | Needs consideration of options and GC decision

## Slide 33: Members Questions – Maintenance
Question | Response
Concerns over proximity of trees and maintenance resulting from leaves falling on the roof | Leaf guards will be provided to the gutters of the structure to prevent any issues with the drainage. The roof will require cleaning, and this will need to be via a cherry picker for access
Maintenance costs | Contractors have been asked to supply : Now updated
Replacement costs | Contractors have been asked to supply : Now updated